## Bug Report
Bug ID | Title | Module | Related Test Cases | Severity | Priority | Steps to Reproduce | Expected Result | Actual Result | Environment / Build | Status | Reported By | Date Reported | attachments
BUG-001 | Previously used valid credentials are auto-filled after a failed login | Login | TC-LOGIN-008 | Low | Low | 1. Log in successfully with valid credentials, then return to the Login page. 2. Enter an invalid username and password and click Login. 3. Observe the login fields. | Previously used valid credentials are not automatically displayed after a failed login. | Login is rejected, but the previously used valid username and password are auto-filled in the fields. Note: may be browser autofill rather than an app defect; verify in a clean profile. |  | Open | Khalid Walid | 28/9 to 5/10 | screenshoots
BUG-002 | Forgot Password with a valid username returns 504 Gateway Timeout | Forgot Password | TC-FP-001 | High | High | 1. On the Login page click Forgot Password. 2. Enter a valid registered username. 3. Click Submit. | A confirmation message is displayed. | Request times out and a 504 Gateway Timeout error is displayed instead of the confirmation message. |  | Open | Khalid Walid | 28/9 to 5/10 | screenshoots
BUG-003 | No duplicate-name warning when adding an employee with an existing First + Last Name | PIM - Add Employee | TC-PIM-009, TC-PIM-0010, TC-PIM-0013 | Medium | Medium | 1. As Admin, go to Add Employee. 2. Enter the same First Name and Last Name as an existing employee. 3. Complete the required fields and click Save. | Employee is added and the duplicate name is flagged/warned (per AC4), without blocking creation. | Employee is added, but no warning or duplicate-name indication is displayed. |  | Open | Khalid Walid | 28/9 to 5/10 | screenshoots
BUG-004 | Sub-unit filter returns employees from other sub-units | Employee List Search/Filter | TC-REQ005-006, TC-REQ005-007 | Medium | Medium | 1. Open the Employee List. 2. Select the Sub-unit "Engineering" (optionally combine with an Employment Status). 3. Apply the filter. | Only employees in the selected Sub-unit are displayed. | Employees from Engineering, QA and Development sub-units are all displayed. Note: confirm whether Engineering is the parent of QA/Development; if the requirement says child units are included, this may be expected behavior. |  | Open | Khalid Walid | 28/9 to 5/10 | screenshoots
BUG-005 | Submitted leave request does not appear in My Leave | Leave Submission | TC-REQ007-01, 07, 08, 09, 10 | High | Critical | 1. Log in as an employee and open the Leave page. 2. Select a leave type, a valid From Date and To Date (also reproduced with From = To). 3. Click Submit. 4. Open My Leave (and refresh). | Leave request is submitted and listed in My Leave with status Pending Approval, and persists after refresh. | Submission appears successful, but My Leave shows "No Records Found"; the request is never listed. Also blocks verification of the leave approval flow (TC-008-xx). |  | Open | Khalid Walid | 28/9 to 5/10 | screenshoots
BUG-006 | Candidate can be added without selecting a Vacancy | Recruitment - Candidates | TC-REQ-009-004 | Medium | Medium | 1. Go to Recruitment > Candidates and click Add. 2. Enter a valid candidate name and email. 3. Leave Vacancy unselected. 4. Click Save. | A validation message is shown for Vacancy and the candidate is not added. | No validation message is shown and the candidate is saved without a vacancy. |  | Open | Khalid Walid | 28/9 to 5/10 | screenshoots
BUG-007 | ESS user can open the Admin module via direct URL | Access Control (ESS vs Admin) | TC-REQ-010-002 | Critical | Critical | 1. Log in with an ESS (non-admin) account. 2. Paste the Admin module URL directly into the browser address bar. 3. Press Enter. | Access is blocked, or the ESS user is redirected to an authorized page. | The Admin Dashboard is displayed to the ESS user. Menu hiding works (TC-REQ-010-001 passed) but server-side authorization is missing. |  | Open | Khalid Walid | 28/9 to 5/10 | screenshoots